## Status Report
Project Name: Plant Pals Operations
Today's date: July 5
Summary |  |  |  | Overall Status (RAG)
We have installed new software to keep track of incoming orders and begun sending out the first test batch of Plant Pals to customers. However, we have run into issues with product quality, customer communication, and the delivery process. Our next milestones include sending the test batch customers newsletters on plant upkeep and sending out the second batch of plants. This report also includes top risks and issues that have arisen and how we intend to take action.
Completed Tasks and Milestones
Description | Date | Status | Owner |  | Comments
Comprar e instalar um novo software para acompanhar os pedidos recebidos | Junho 15 | Completed | IT Specialist |  | A instalação levou três dias a mais do que o esperado.
Began sending test batches of Plant Pals orders to customers | June 21 | Completed | Diretor de acompanhamento |  | The number of orders exceeded targets by 15%.
Upcoming Tasks and Milestones
Description | Date | Status | Owner |  | Comments
Send the first batch customers e-newsletters on how to take care of their plants. | Julho 7 | Upcoming | Gerente de serviços ao cliente |  | The newsletter must follow Office Green’s brand design guidelines.
Conseguir pelo menos 95% das datas de entrega | July 19 | Upcoming | Fulfillment Director |  | A taxa de erro precisa ser inferior a 5%
Top Risks and Issues
Issue |  | Impact | Action |  |  | Owner
A equipe do armazém informou que 10% das plantas não foram colocadas no vaso da maneira adequada |  | Profit loss, complaints, and budget issues | Avaliar e ajustar o processo de envasamento das plantas |  |  | Warehouse Operations Manager
The customer relations team is receiving only 30% of requests and complaints |  | Customer dissatisfaction | Fix problems with new customer service software |  |  | especialista de TI
A taxa de conclusão de entrega atual é de apenas 80% |  | Assinaturas canceladas | Hire and train more delivery drivers |  |  | HR Specialist