## Dashboard
Project Name: Plano de Treinamento e Operações do Plant Pals da Office Green
Description:
Owner: Julio Leite
Status: Draft/Active/Inactive
Key Docs | Description
Project charter | Termo de abertura do projeto, aqui é o plano que temos que seguir para que tudo de certo.
Statement of work | descreve os produtos e serviços a serem fornecidos.
Risk management plan | Aqui temos os riscos de nosso projeto e como mitigalos
Schedule | Cronograma do nosso projeto
Budget | Orçamento do projeto
Communication plan | Como devemos nos comunicar
Shared folder | Pasta com toda a documentação do projeto
RACI chart | Grafico que define os "Atores e seu papel dentro do projeto"

## Project Schedule
Gantt Chart
TITLE: Plant Pals Operations and Training Plan | [6 empty] | COMPANY NAME: |  |  |  |  | Office Green
PROJECT MANAGER: [Name] | [6 empty] | CREATION DATE: |  |  |  |  | 02/15
TASK ID NUMBER | MILESTONES & TASKS | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [29 empty] | PHASE TWO | [14 empty] | PHASE THREE
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[7 empty] | MARCH | [22 empty] | APRIL | [21 empty] | MAY | [20 empty] | JUNE
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Estabelecer um plano de entrega e logística da fábrica | [5 empty] | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11
1.1 | Conseguir materiais para embalagens | diretor de atendimento | 3/1 | 3/12 | 10 | 0% | bar: MARCH M 1 to MARCH F 12
1.2 | Contratar motoristas para entregas | especialista de recursos humanos | 3/15 | 3/26 | 10 | 0% | bar: MARCH M 15 to MARCH F 26
1.3 | Calcular as taxas de entrega | analista financeiro | 3/29 | 4/9 | 10 | 0% | bar: MARCH M 29 to APRIL F 9
2 | Selecionar e instalar software e equipamentos da cadeia de suprimentos
2.1 | Supervisionar a configuração do fornecedor de gerenciamento de estoque e software de atendimento | gerente de estoque | 4/12 | 4/14 | 3 | 0% | bar: APRIL M 12 to APRIL W 14
2.2 | Supervisionar a instalação do fornecedor de equipamento de atendimento | diretor de atendimento | 4/15 | 4/16 | 2 | 0% | bar: APRIL R 15 to APRIL F 16
2.3 | Determinar protocolos internos de segurança para os equipamentos | testador de garantia de qualidade | 4/19 | 4/30 | 10 | 0% | bar: APRIL M 19 to APRIL F 30
3 | Desenvolver e lançar um programa de treinamento de funcionários
3.1 | Desenvolver sessões de treinamento | gerente de treinamento | 5/3 | 5/14 | 10 | 0% | bar: MAY M 3 to MAY F 14
3.2 | Treinar funcionários para usar o software e os equipamentos | gerente de treinamento | 5/17 | 5/28 | 10 | 0% | bar: MAY M 17 to MAY F 28
3.3 | Monitorar o progresso dos funcionários e melhorar os processos de treinamento | gerente de treinamento | 5/31 | 6/11 | 10 | 0% | bar: MAY M 31 to JUNE F 11

## Communication Plan
Project Plant Pals: Employee Training Communication Plan
Recipients | Type of Communication | Frequency | Sender/Owner | Key Dates | Delivery Method | Goal | Resource Links | Notes
Core Team | Planning Meeting | Daily | Project Manager | Every day at 3pm | In Person | Project planning and task updates to make sure the team stays on track | [link to meeting agenda and notes] | If needed, check in with manager about any high-level questions before meetings.
Software and Equipment Vendor | Planning Meeting | One time | Core Team: Training Manager | No inicio do projeto | In Person | Go over the training manual in order to create an effective training plan for Office Green's employees
Human Resources | Planning Check-In | Weekly | Core Team: Training Manager |  | In Person | Project planning assistance; provide support during the training session
Facilities | Planning Check-In | Weekly | Core Team: HR Specialist & Training Manager | No inicio do proejto | Phone Call | Reserve rooms, spaces, and equipment needed for employee training
Print Shop | Planning Check-In | Weekly | Core Team: Administrative Coordinator | No inicio do proejto | Phone Call | Coordinate on the printing and delivery of training manuals for employees
Office Green employees | Informational Update | Weekly | Core Team: HR Specialist | No inicio do proejto | Email (from company address) | Communicate schedules, locations, and other necessary details to trainees
Office Green employees | Training | Daily | Core Team: Training Manager | No inicio do proejto | In Person | Train employees to use the supply chain management software and equipment
Office Green employees | Survey | One time | Core Team: HR Specialist & Training Manager | sempre após o treinamento | Email (from company address) | Post-training survey
Your Manager | Status Update | Weekly | Project Manager | No inicio da semana | In Person | Update on event planning, ask questions, and get feedback
Senior Leaders: Director of Operations and the Director of Product (and CC your manager) | Status Update | One time | Core Team: Administrative Coordinator | No inicio da semana | Email (from individual address) | High-level information and general updates

## Budget
Budget: Project Plant Pals Operations & Training
[7 empty] | TARGET BUDGET | ACTUAL/ FINAL SPEND | UNDER/ OVER
[7 empty] | 62000 | 0 | 62000
| LABOR |  |  | MATERIALS |  | FIXED COST | BUDGET | ACTUAL | UNDER/OVER
MILESTONES & TASKS | EMPLOYEE DETAILS | HOURS | RATE | UNITS | $/UNIT
Marco 1: Estabelecer um plano de entrega e logística das plantas
Tarefa 1: Comprar caminhões de entrega |  |  |  | 2 | 15000 |  | 30000 |  | -30000
Tarefa 2: Conseguir matéria para embalagens |  |  |  | 1500 | 2 |  | 3000 |  | -3000
Tarefa 3:Pagar os motoristas de entregas | dois motoristas de entregas | 160 | 15 |  |  |  | 2400 |  | -2400
-- | [5 empty] | Total | 35400 | 0
Marco 2: Selecionar e instalar equipamento e software de gestão da cadeia de abastecimento.
Tarefa 1: Encontrar fornecedor | [5 empty] | 15000 | 15000 |  | -15000
-- | [5 empty] | Total | 15000 | 0
Marco 3: Desenvolver e lançar um programa de treinamento de funcionários.
Tarefa 1: Desenvolver sessões de treinamento | especialista | 80 | 50 |  |  |  | 4000 |  | -4000
Tarefa 2:Treinar funcionários para usar o software e os equipamentos. | gerente | 80 | 25 |  |  |  | 2000 |  | -2000
Tarefa 3:Monitorar o progresso dos funcionários e melhorar os processos de treinamento. | gerente | 80 | 25 |  |  |  | 2000 |  | -2000
-- | [5 empty] | Total | 8000 | 0
Reserve buffer | [6 empty] | 3600
TOTAL | [6 empty] | 62000 | 0